## Sheet1
Requirements |  | Priority | Task Completion Status % | Allocation
Django side:
Creating the movie database with required fields. | API end points | High | 50 | Vijoy
Creating ticket table for each user that comes for booking. |  | High | 0 | Ashok/Sai
Creating a theatre table to load theatre. |  | High | 0 | Ashok/Sai
Angular side:
Creating the login for a new user registraion with required fields |  | High | 0 | Sindhu
Creating the login page for already registered user to proceed with movies booking. |  | High | 0 | Sindhu
After login the flow should be either admin or user depending on the credentials. |  | High | 0 | Sindhu
The user can choose the available movies (GET API) which are fetched from backend. |  | High | 90 | Vijoy
Once the user clicks on a specific movie, its description/price/theatre info will be available (movie detils). |  | High | 35 | Vijoy
Display invoice and ask for confirmation to complete the transaction , here the (API POST) will do the insertion to tickets table in djnago. |  | High | 0
The user has to get the ticket thru email that he registered while login reg. |  | Low | 0
We are planning for interactive pannel to display for the available seats . |  | Low

## Sheet2
Manoge Sebastian George(UST,IN) <Manoge.George@ust.com>; Vasuki Dhulkhed(UST,IN) <Vasuki.Dhulkhed@ust.com>; Ann Sherin Antony(UST,IN) <ann.sherin@ust.com>; Sonia Mary Anthony(UST,IN) <Sonia.Anthony@ust.com>; Rekha Muraleedharan(UST,IN) <Rekha.Muraleedharan@ust.com>; Hima Kurian(UST,IN) <Hima.Kurian@ust.com>; Arunraj Rajendran Anitha(UST,IN) <Arunraj.Rajendrananitha@ust.com>; Dhanya Padmini(UST,IN) <Dhanya.Padmini@ust.com>; Sreyasmon Shaji(UST,IN) <Sreyasmon.Shaji@ust.com>; Vignesh Kamaraj(UST,IN) <Vignesh.K2@ust.com>; Vignesh Paranthaman(UST,IN) <Vignesh.Paranthaman@ust.com>; Mani Kumari Gudala(UST,IN) <Mani.Gudala@ust.com>; Sindhuja Chunchu(UST,IN) <Sindhuja.Chunchu@ust.com>; Vinodh Ganesan(UST,IN) <Vinodh.G@ust.com>; Vishnu Dev(UST,IN) <Vishnu.Dev@ust.com>; Niharika Venkatesh(UST,IN) <Niharika.Venkatesh@ust.com>; Lavanya Subramanian(UST,IN) <Lavanya.Subramanian@ust.com>; Rini Jones(UST,IN) <Rini.Jones@ust.com>; Likhitha Varma(UST,IN) <Likhitha.Varma@ust.com>; Vijaykumar Chilla(UST,IN) <Vijaykumar.Chilla@ust.com>; Vignesh Periyasamy(UST,IN) <Vignesh.Periyasamy@ust.com>; Jyoti Singh(UST,IN) <Jyoti.Singh@ust.com>; Praveen Parambudur(UST,IN) <SriParambudur.Praveen@ust.com>; Kavya Kumari(UST,IN) <Kavya.Kumari@ust.com>; Swetha Maadhav(UST,IN) <Swetha.Maadhav@ust.com>; Divya Dande(UST,IN) <Divya.D@ust.com>; Sravani Parimi(UST,IN) <Sravani.Parimi@ust.com>; Sakshi Rahul Chimdyalwar(UST,IN) <Sakshi.RahulChimdyalwar@ust.com>; Arundhati Pulitharanikathil Girivasan(UST,IN) <Arundhati.Pulitharanikathilgirivasan@ust.com>; Akshay Prasanth(UST,IN) <Akshay.Prasanth@ust.com>; Saikiranreddy Beereddy(UST,IN) <SaiKiranReddy.Beereddy@ust.com>; Suneel Neelakantam(UST,IN) <Suneelkumar.Neelakantam@ust.com>; Vidya Gopi(UST,IN) <Vidya.Gopi@ust.com>; Lakshmi Konamma Manduru(UST,IN) <Lakshmi.KonammaM@ust.com>; Parvathi Devi Edupuganti(UST,IN) <Edupuganti.ParvathiDevi@ust.com>; Vijoy Joseph(UST,IN) <Vijoy.Joseph@ust.com>; Suhana Malayil(UST,IN) <Suhana.Malayil@ust.com>; Devika Aneesh(UST,IN) <Devika.Aneesh@ust.com>; Sandra Surendran(UST,IN) <Sandra.Surendran@ust.com>; Anagha Kelembeth(UST,IN) <Anagha.Kelembeth@ust.com>; Adarsh Babukuttan(UST,IN) <Adarsh.Babukuttan@ust.com>